## Data Requirements
Source Table | Column / Field | Source System / EDI | Data Type | Description / Role in Model | MVP Required? | Phase | Grain | Notes
Medical Claims (837P/837I) | claim_id | CLM01 | VARCHAR | Claim grain identifier / join key | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | member_id | Box 1a (CMS-1500) | VARCHAR | Join key to enrollment; primary member key | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | service_from_date | Box 24A | DATE | Service start date — used for time windowing features | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | service_to_date | Box 24A | DATE | Service end date — LOS calculation for inpatient stays | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | icd10_dx_1 through icd10_dx_12 | Box 21 (A-L) | VARCHAR | Diagnosis codes for HCC risk scoring, chronic condition flags | Yes | 1 - MVP | Claim | Up to 12 Dx per claim
Medical Claims (837P/837I) | cpt_hcpcs | Box 24D | VARCHAR | Procedure code — service type classification (surgery, imaging, lab, etc.) | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | cpt_modifier_1 through cpt_modifier_4 | Box 24D | VARCHAR | Procedure modifiers — context for telehealth, bilateral, etc. | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | place_of_service | Box 24B | VARCHAR | IP/OP/ER/Office classification (POS codes 11,21,22,23,51,61) | Yes | 1 - MVP | Claim | Key for utilization type features
Medical Claims (837P/837I) | billed_amount | Box 28 | DECIMAL | Charge amount — inflation signal | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | allowed_amount | 835 Adjudication | DECIMAL | Primary cost measure for all cost features | Yes | 1 - MVP | Claim | Most predictive cost field
Medical Claims (837P/837I) | paid_amount | 835 | DECIMAL | Net plan payment amount | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | member_liability | 835 (deductible+copay+coins) | DECIMAL | Member cost-sharing — deductible exhaustion signal | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | rendering_provider_npi | Box 24J | VARCHAR | Provider efficiency linkage — unique provider counts | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | billing_provider_npi | Box 33 | VARCHAR | Provider organization — AMC/teaching hospital flag | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | drg_code | UB-04 (institutional) | VARCHAR | Inpatient case mix classification | Yes | 1 - MVP | Claim | Institutional claims only
Medical Claims (837P/837I) | revenue_code | UB-04 (institutional) | VARCHAR | Facility service type (e.g., 0762 = observation hours) | Yes | 1 - MVP | Claim | Institutional claims only
Medical Claims (837P/837I) | admission_type | UB-04 | VARCHAR | Emergency vs. elective admission classification | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | discharge_status | UB-04 | VARCHAR | Discharge disposition (SNF/home/expired) — post-acute trajectory | Yes | 1 - MVP | Claim
Medical Claims (837P/837I) | claim_status | Adjudication | VARCHAR | Paid/denied/adjusted — filter to paid claims for features | Yes | 1 - MVP | Claim
Member Enrollment (834) | member_id | 834 Transaction | VARCHAR | Primary key — join to claims | Yes | 1 - MVP | Member
Member Enrollment (834) | date_of_birth | 834 Transaction | DATE | Age calculation → age bands (0-17, 18-25, …85+) | Yes | 1 - MVP | Member
Member Enrollment (834) | gender | 834 Transaction | VARCHAR | Age-sex risk factor | Yes | 1 - MVP | Member | M / F
Member Enrollment (834) | plan_type | 834 Transaction | VARCHAR | HMO/PPO/EPO/HDHP/MA segmentation | Yes | 1 - MVP | Member
Member Enrollment (834) | metal_level | 834 Transaction | VARCHAR | ACA benefit richness (Bronze/Silver/Gold/Platinum) | Yes | 1 - MVP | Member | ACA plans only
Member Enrollment (834) | effective_date | 834 Transaction | DATE | Enrollment start — tenure calculation | Yes | 1 - MVP | Member
Member Enrollment (834) | term_date | 834 Transaction | DATE | Enrollment end — member months; churn signal | Yes | 1 - MVP | Member | NULL if active
Member Enrollment (834) | zip_code | 834 Transaction | VARCHAR | Geographic risk factor; SDOH linkage key | Yes | 1 - MVP | Member | 5-digit ZIP
Member Enrollment (834) | county_fips | 834 Transaction | VARCHAR | Geographic adjustment factor | Yes | 1 - MVP | Member
Member Enrollment (834) | group_id | 834 Transaction | VARCHAR | Employer group — experience rating; group size band | Yes | 1 - MVP | Member
Member Enrollment (834) | pcp_npi | 834 Transaction | VARCHAR | Medical home attribution — PCP efficiency linkage | Yes | 1 - MVP | Member | NULL if unattributed
Member Enrollment (834) | risk_score | CMS-HCC calculation | DECIMAL | Prospective HCC risk score | Yes | 1 - MVP | Member | Updated annually
Member Enrollment (834) | lob | 834 Transaction | VARCHAR | Commercial / Medicare Advantage / Medicaid segmentation | Yes | 1 - MVP | Member
Adjustments/Remittance (835) | claim_id | 835 Transaction | VARCHAR | Join key to medical claims | Yes | 1 - MVP | Claim
Adjustments/Remittance (835) | adjustment_reason_code | 835 Transaction | VARCHAR | Denial type (CO, PR, OA) — denial pattern features | Yes | 1 - MVP | Claim | CAS segment
Adjustments/Remittance (835) | paid_date | 835 Transaction | DATE | Payment lag → IBNR signal; claim maturity | Yes | 1 - MVP | Claim
Adjustments/Remittance (835) | deductible_applied | 835 Transaction | DECIMAL | Deductible exhaustion tracking | Yes | 1 - MVP | Claim
Adjustments/Remittance (835) | copay_amount | 835 Transaction | DECIMAL | Member cost-sharing — copay component | Yes | 1 - MVP | Claim
Adjustments/Remittance (835) | coinsurance_amount | 835 Transaction | DECIMAL | Member financial exposure — coinsurance component | Yes | 1 - MVP | Claim
Pharmacy Claims | member_id | NCPDP / Pharmacy PBM | VARCHAR | Join to enrollment | Nice-to-Have | 2 - Enhancement | Claim | From PBM feed
Pharmacy Claims | ndc_code | NCPDP | VARCHAR | Drug identification — specialty Rx flag, polypharmacy | Nice-to-Have | 2 - Enhancement | Claim | 11-digit NDC
Pharmacy Claims | therapeutic_class | PBM / First DataBank | VARCHAR | Drug classification — polypharmacy calculation | Nice-to-Have | 2 - Enhancement | Claim
Pharmacy Claims | allowed_amount | PBM Adjudication | DECIMAL | Pharmacy cost — specialty Rx spend | Nice-to-Have | 2 - Enhancement | Claim
Pharmacy Claims | fill_date | NCPDP | DATE | Prescription fill date — time windowing | Nice-to-Have | 2 - Enhancement | Claim
Pharmacy Claims | days_supply | NCPDP | INTEGER | Medication adherence signal | Nice-to-Have | 2 - Enhancement | Claim
Auth / UM Data | auth_id | UM System | VARCHAR | Authorization identifier | Nice-to-Have | 2 - Enhancement | Auth
Auth / UM Data | auth_type | UM System | VARCHAR | Prior auth / concurrent / retrospective | Nice-to-Have | 2 - Enhancement | Auth
Auth / UM Data | auth_status | UM System | VARCHAR | Approved / denied / pended | Nice-to-Have | 2 - Enhancement | Auth
Auth / UM Data | requested_service | UM System | VARCHAR | CPT/HCPCS of requested procedure | Nice-to-Have | 2 - Enhancement | Auth
SDOH (Free Sources) | adi_national_rank | Neighborhood Atlas | INTEGER | Area Deprivation Index percentile (1-100) | Nice-to-Have | 2 - Enhancement | ZIP/Tract | Free download
SDOH (Free Sources) | svi_overall_score | CDC SVI | DECIMAL | Social Vulnerability Index composite (0-1) | Nice-to-Have | 2 - Enhancement | Census Tract | Free download
SDOH (Free Sources) | median_household_income | ACS B19013 | DECIMAL | Median household income for member ZCTA | Nice-to-Have | 2 - Enhancement | ZCTA | Free download
SDOH (Free Sources) | food_desert_flag | USDA Food Atlas | INTEGER | Low income / low access (LILA) flag | Nice-to-Have | 2 - Enhancement | Census Tract | Free download
SDOH (Free Sources) | hpsa_primary_care_flag | HRSA HPSA | INTEGER | Health Professional Shortage Area designation | Nice-to-Have | 2 - Enhancement | County | Free download
Call Center Data | call_transcripts | IVR / CRM | TEXT | Call center transcripts for NLP feature extraction | Nice-to-Have | 3 - Future | Call | Requires NLP pipeline

## Detailed Project Plan
Task ID | Phase | Week | Day | Task Name | Detailed Description | Deliverable / Output | Owner / Role | Dependencies | Est. Hours | Status
1.1 | Data & Features | Week 1 | Monday | Extract Medical Claims (24 months) | Pull 24 months of 837P (professional) and 837I (institutional) claims into analytics environment. Include all fields: claim_id, member_id, service dates, ICD-10 Dx (1-12), CPT/HCPCS, POS, billed/allowed/paid amounts, provider NPIs, DRG, revenue codes, admission/discharge info. | Raw medical claims table in analytics data store | Data Engineer | Access to claims data warehouse | 8 | Not Started
1.2 | Data & Features | Week 1 | Monday | Extract Adjustments/Remittance (835) | Pull 835 remittance data for same 24-month window. Include adjustment reason codes, paid dates, deductible/copay/coinsurance amounts. Join to claims on claim_id. | Adjustments table joined to claims | Data Engineer | Task 1.1 | 4 | Not Started
1.3 | Data & Features | Week 1 | Tuesday | Extract Member Enrollment (834) | Pull enrollment/eligibility data for all members with claims in the 24-month window. Include demographics (DOB, gender), plan info (type, metal level, LOB), dates (effective, term), geographic (ZIP, county FIPS), PCP attribution, risk scores, group ID. | Member enrollment table with demographics | Data Engineer | Task 1.1 | 6 | Not Started
1.4 | Data & Features | Week 1 | Tuesday | Build Member-Month Spine | Create member-month grain table: one row per member per month of enrollment. Calculate enrollment tenure, new member flag, continuous enrollment months. This becomes the modeling grain for all features. | Member-month spine table (primary key: member_id + month) | Data Engineer | Task 1.3 | 4 | Not Started
1.5 | Data & Features | Week 1 | Wednesday | Build Cost Features (Category A: 15 features) | Calculate all 15 cost features over rolling windows (3m, 6m, 12m): total_allowed, total_paid, cost_trend_slope, cost_acceleration, max_single_claim, pct_cost_in_last_3m, IP/OP/ER/Rx allowed, specialty_rx_flag, member_oop, deductible_exhausted. | Cost feature table (15 columns per member-month) | Data Scientist | Tasks 1.1, 1.2, 1.4 | 8 | Not Started
1.6 | Data & Features | Week 1 | Thursday | Build Utilization Features (Category B: 20 features) | Calculate 20 utilization features: IP admits, IP days, ER visits (12m + 3m), OP/office visits, unique providers, unique specialties, imaging/lab/surgery counts, readmit_30day_flag, avg_los, observation hours, SNF days, home health, telehealth, DME, ambulance, utilization_trend_slope. | Utilization feature table (20 columns per member-month) | Data Scientist | Tasks 1.1, 1.4 | 8 | Not Started
1.7 | Data & Features | Week 1 | Friday | Build Clinical Features (Category C: 20 features) | Calculate 20 clinical features from ICD-10 codes: HCC risk score + change, unique HCC count, chronic condition count, 10 individual condition flags (diabetes, CHF, CKD, COPD, cancer, MH, SUD, transplant, obesity, pregnancy), trauma flag, new cancer/ESRD Dx flags, Elixhauser index, polypharmacy flag, high-risk combination flag. | Clinical feature table (20 columns per member-month) | Data Scientist | Tasks 1.1, 1.4 | 8 | Not Started
1.8 | Data & Features | Week 1 | Friday | Data Quality Audit | Run completeness checks on all extracted tables: % NULL for each column, distribution analysis, outlier detection, ICD-10 coding consistency. Document data quality issues and imputation strategy. | Data quality audit report; imputation strategy document | Data Scientist | Tasks 1.1-1.7 | 4 | Not Started
2.1 | Model Training | Week 2 | Monday | Build Demographics & Plan Features (Category D: 15 features) | Calculate 15 demographic and plan design features: age, age_band, gender, plan_type, metal_level, LOB, enrollment_tenure, new_member_flag, deductible_amount, oop_max, coinsurance_rate, network_type, pcp_attributed, group_size_band, dependent_flag. | Demographics feature table (15 columns per member-month) | Data Scientist | Task 1.3, 1.4 | 4 | Not Started
2.2 | Model Training | Week 2 | Monday | Build Provider Features (Category E: 10 features) | Calculate 10 provider/network features: pcp_efficiency_score, OON claim/cost %, PCP visit count, specialist referral count, high_cost_provider_flag, AMC flag, provider_density, distance_to_pcp, usual_source_of_care. | Provider feature table (10 columns per member-month) | Data Scientist | Tasks 1.1, 1.3, 1.4 | 4 | Not Started
2.3 | Model Training | Week 2 | Monday | Assemble Full Feature Matrix | Join all 6 feature category tables (A-F) onto member-month spine. Create target variable: next-quarter total allowed >= $50K binary flag. Apply time-based train/validation/test split (Q1-Q2 2024 train, Q3 2024 validation, Q4 2024 test). Final matrix: ~85 features, ~10M rows. | Complete 85-feature matrix with target variable; train/val/test splits | Data Scientist | Tasks 1.5-1.7, 2.1-2.2 | 6 | Not Started
2.4 | Model Training | Week 2 | Tuesday | Train Stage 1: XGBoost Binary Classifier (Baseline) | Train XGBoost with initial hyperparameters: max_depth=6, lr=0.05, n_estimators=500, scale_pos_weight=45. Run 5-fold time-series cross-validation. Evaluate baseline AUC-ROC, AUC-PR, recall@10%, capture rate. Generate feature importance ranking. | Baseline Stage 1 model; AUC metrics; feature importance plot | Data Scientist | Task 2.3 | 8 | Not Started
2.5 | Model Training | Week 2 | Wednesday | Hyperparameter Tuning (Optuna) | Run 100-trial Optuna optimization for XGBoost: tune max_depth (4-8), learning_rate (0.01-0.1), n_estimators (200-1000), subsample (0.6-1.0), colsample_bytree (0.6-1.0), min_child_weight (10-100), reg_alpha, reg_lambda. Compare SMOTE vs. scale_pos_weight. Target: AUC-ROC > 0.85, AUC-PR > 0.40. | Tuned Stage 1 model; optimization history; best parameters | Data Scientist | Task 2.4 | 8 | Not Started
2.6 | Model Training | Week 2 | Thursday | Train Stage 2: LightGBM Cost Regression | Filter to members with Stage 1 P(high-cost) >= 0.30. Train LightGBM regression on log-transformed next-quarter allowed amount. Tune: num_leaves (31-127), learning_rate (0.01-0.05), feature_fraction, bagging_fraction. Evaluate MAPE, R-squared, aggregate accuracy. | Stage 2 regression model; cost prediction metrics; back-transform validation | Data Scientist | Task 2.5 | 8 | Not Started
2.7 | Model Training | Week 2 | Friday | Generate SHAP Explanations & Sanity Check | Compute SHAP values using TreeExplainer for both stages. Generate global beeswarm plot (top 15 features), individual waterfall plots for sample members, force plots. Review with clinical SME: do top drivers make clinical sense? Flag any counterintuitive patterns. | SHAP analysis report; beeswarm plot; sample waterfall plots; clinical sanity check notes | Data Scientist + Medical Director | Tasks 2.5, 2.6 | 8 | Not Started
3.1 | Validation | Week 3 | Monday | Out-of-Time Holdout Validation (Q4 2024) | Score Q4 2024 holdout set with both Stage 1 and Stage 2 models. Compute all metrics from Section 5: AUC-ROC, AUC-PR, Recall@10%, Recall@5%, Capture Rate, MAPE, R-squared, Aggregate Accuracy, Decile Calibration. Compare predicted vs. actual spend at aggregate and decile level. | Comprehensive validation report with all metrics; decile calibration chart | Data Scientist | Tasks 2.5, 2.6 | 8 | Not Started
3.2 | Validation | Week 3 | Tuesday | Download & Join SDOH Data (Free Sources) | Download: (1) CDC SVI from ATSDR, (2) ADI from Neighborhood Atlas, (3) ACS median income from Census, (4) USDA Food Atlas LILA flags, (5) HRSA HPSA designations. Map member ZIP/tract/county to SDOH features. Join to feature matrix as Category F (5 features). | 5 SDOH features joined to feature matrix; source documentation | Data Engineer | Task 1.4 | 8 | Not Started
3.3 | Validation | Week 3 | Wednesday | Retrain with SDOH Features & Measure Lift | Retrain both Stage 1 and Stage 2 models with full 85+5 SDOH features. Compare A/B: model with vs. without SDOH. Measure marginal AUC lift, MAPE improvement. Document whether SDOH features provide meaningful predictive value. | A/B comparison report; decision on SDOH inclusion; retrained models | Data Scientist | Tasks 3.1, 3.2 | 8 | Not Started
3.4 | Validation | Week 3 | Thursday | Calibration Analysis | Generate calibration curves: predicted probabilities vs. actual event rates across deciles. If miscalibrated, apply Platt scaling or isotonic regression. Verify that predicted spend monotonically increases across actual spend deciles. | Calibration curve plots; Platt scaling parameters if needed; calibrated model | Data Scientist | Task 3.3 | 6 | Not Started
3.5 | Validation | Week 3 | Friday | Fairness Audit | Evaluate model performance across protected categories: race/ethnicity (if available), gender, age bands, geographic regions, ADI quintiles. Check for disparate impact: are false negative rates similar across groups? Apply equalized odds corrections if disparities found. | Fairness audit report; disparity metrics; remediation plan if needed | Data Scientist + Compliance | Task 3.3 | 8 | Not Started
4.1 | Productionize | Week 4 | Monday | Build Production Scoring Pipeline | Build automated batch scoring pipeline: (1) Extract fresh claims/enrollment data, (2) Compute features using same engineering logic, (3) Score with Stage 1 + Stage 2 models, (4) Generate SHAP explanations for flagged members, (5) Assign risk tiers. Schedule: monthly full refresh, weekly incremental for CM teams. | Automated scoring pipeline (Airflow/Databricks job); schedule configuration | ML Engineer | Tasks 2.5, 2.6, 3.3 | 8 | Not Started
4.2 | Productionize | Week 4 | Tuesday | Build Output Table & Risk Tier Logic | Create published output table with columns: member_id, prob_high_cost, predicted_spend, ci_lower, ci_upper, risk_tier (CRITICAL/HIGH/ELEVATED/WATCH/STANDARD), top_3_drivers (from SHAP), cm_assigned, last_updated. Implement tier thresholds: CRITICAL >0.70, HIGH 0.50-0.70, ELEVATED 0.30-0.50, WATCH 0.15-0.30, STANDARD <0.15. | Published member_risk_score table; tier assignment logic; CI computation | ML Engineer + Data Engineer | Task 4.1 | 8 | Not Started
4.3 | Productionize | Week 4 | Wednesday | Build Interactive Dashboard | Build Tableau/Power BI dashboard with: (1) Executive summary KPI cards (Critical/High counts, total pool estimate), (2) Top spend drivers chart, (3) Risk tier distribution, (4) Member detail table with search/filter, (5) SHAP waterfall drilldown per member, (6) Predicted vs. actual trend (rolling 8 quarters). | Interactive dashboard (Tableau/Power BI); user guide | BI Developer | Task 4.2 | 8 | Not Started
4.4 | Productionize | Week 4 | Wednesday | Set Up Model Monitoring | Implement PSI (Population Stability Index) monitoring for feature distributions and prediction distributions. Set alert thresholds: PSI > 0.1 = warning, > 0.2 = action required. Configure quarterly model retraining schedule. Set up performance tracking dashboard. | Model monitoring dashboard; PSI alerts; retraining schedule | ML Engineer | Task 4.1 | 4 | Not Started
4.5 | Productionize | Week 4 | Thursday | Stakeholder Review & Threshold Refinement | Present results to Care Management, Actuarial, Medical Director, and executive sponsors. Walk through: model performance metrics, sample member predictions with SHAP explanations, dashboard demo, risk tier distribution. Collect feedback on tier thresholds, CM capacity alignment, and prioritization logic. | Stakeholder feedback; refined tier thresholds; sign-off document | Data Scientist + Project Lead | Tasks 4.2, 4.3 | 8 | Not Started
4.6 | Productionize | Week 4 | Friday | Production Go-Live: First Scoring Run | Execute first production scoring run. Deliver scored member risk list to CM team. Validate output table completeness and accuracy. Confirm dashboard is live and accessible. Document runbook for ongoing operations. | MVP LIVE: First production member risk list delivered to CM; operational runbook | Full Team | Tasks 4.1-4.5 | 8 | Not Started
4.7 | Productionize | Week 4 | Friday | Post-Go-Live: Define Phase 2 Roadmap | Document Phase 2 enhancements: (1) Add pharmacy claims for specialty Rx and polypharmacy, (2) Integrate Auth/UM data, (3) Build NLP features from call center transcripts, (4) Real-time scoring API, (5) A/B testing framework for CM interventions, (6) IBNR integration with actuarial models. | Phase 2 roadmap document; prioritized backlog | Project Lead | Task 4.6 | 4 | Not Started

## Provider Scoring - Data Reqs
Source Table | Column / Field | Source System | Data Type | Description / Role in Model | Required? | Phase | Grain | Notes
Provider Master (NPPES) | provider_npi | CMS NPPES | VARCHAR | National Provider Identifier — primary key for provider-level scoring | Yes | 1 - MVP | Provider | 10-digit NPI
Provider Master (NPPES) | provider_name | NPPES / Credentialing | VARCHAR | Provider or organization name | Yes | 1 - MVP | Provider
Provider Master (NPPES) | entity_type | NPPES | VARCHAR | Individual (Type 1) vs. Organization (Type 2) | Yes | 1 - MVP | Provider | Key for clustering
Provider Master (NPPES) | primary_taxonomy | NPPES | VARCHAR | Provider specialty taxonomy code (e.g., 207R00000X = Internal Medicine) | Yes | 1 - MVP | Provider | Maps to specialty grouping
Provider Master (NPPES) | specialty_description | NPPES / Taxonomy crosswalk | VARCHAR | Human-readable specialty (Cardiology, Oncology, etc.) | Yes | 1 - MVP | Provider | Used in embedding/clustering
Provider Master (NPPES) | practice_address | NPPES | VARCHAR | Street address of primary practice location | Yes | 1 - MVP | Provider
Provider Master (NPPES) | practice_city | NPPES | VARCHAR | City of primary practice | Yes | 1 - MVP | Provider | Geo clustering
Provider Master (NPPES) | practice_state | NPPES | VARCHAR | State of primary practice | Yes | 1 - MVP | Provider | Geo clustering
Provider Master (NPPES) | practice_zip | NPPES | VARCHAR | ZIP code of primary practice — geo embedding key | Yes | 1 - MVP | Provider | 5-digit ZIP
Provider Master (NPPES) | practice_county_fips | NPPES / Census crosswalk | VARCHAR | County FIPS for geographic adjustment | Yes | 1 - MVP | Provider
Provider Master (NPPES) | hospital_affiliation | Credentialing / PECOS | VARCHAR | Affiliated hospital system or health system | Nice-to-Have | 2 - Enhancement | Provider
Provider Master (NPPES) | teaching_hospital_flag | CMS IME/GME list | INTEGER | Academic medical center / teaching hospital indicator | Nice-to-Have | 2 - Enhancement | Provider
Provider Master (NPPES) | group_practice_size | PECOS / Internal | INTEGER | Number of providers in practice group | Nice-to-Have | 2 - Enhancement | Provider | Small/Mid/Large
Provider Claims Aggregates | total_claims_12m | Claims Data Warehouse | INTEGER | Total claim lines submitted by provider in 12 months | Yes | 1 - MVP | Provider | Volume indicator
Provider Claims Aggregates | total_allowed_12m | Claims Data Warehouse | DECIMAL | Total allowed amount for provider in 12 months | Yes | 1 - MVP | Provider | Cost volume
Provider Claims Aggregates | total_paid_12m | Claims Data Warehouse | DECIMAL | Total paid amount for provider in 12 months | Yes | 1 - MVP | Provider | Net cost
Provider Claims Aggregates | unique_members_12m | Claims Data Warehouse | INTEGER | Distinct members seen by provider in 12 months | Yes | 1 - MVP | Provider | Panel size
Provider Claims Aggregates | avg_allowed_per_claim | Claims Data Warehouse | DECIMAL | Average allowed per claim line — cost efficiency signal | Yes | 1 - MVP | Provider | Key economic metric
Provider Claims Aggregates | avg_allowed_per_member | Claims Data Warehouse | DECIMAL | Average allowed per unique member (PMPY equivalent) | Yes | 1 - MVP | Provider | Risk-adjusted cost comparison
Provider Claims Aggregates | ip_admit_rate | Claims Data Warehouse | DECIMAL | Inpatient admission rate per 1000 members attributed | Yes | 1 - MVP | Provider | Utilization efficiency
Provider Claims Aggregates | er_visit_rate | Claims Data Warehouse | DECIMAL | ER visit rate per 1000 members attributed | Yes | 1 - MVP | Provider | Avoidable ER signal
Provider Claims Aggregates | readmit_30day_rate | Claims Data Warehouse | DECIMAL | 30-day readmission rate for provider's patients | Yes | 1 - MVP | Provider | Quality metric
Provider Claims Aggregates | avg_los | Claims Data Warehouse | DECIMAL | Average length of stay for inpatient admissions | Yes | 1 - MVP | Provider | Institutional only
Provider Claims Aggregates | high_cost_member_pct | Member Risk Score Table | DECIMAL | % of provider's panel flagged CRITICAL/HIGH by member scoring | Yes | 1 - MVP | Provider | Cross-input from member model
Provider Claims Aggregates | avg_member_risk_score | Member Risk Score Table | DECIMAL | Average member risk score across provider's panel | Yes | 1 - MVP | Provider | Cross-input from member model
Provider Claims Aggregates | specialty_rx_pct | Pharmacy Claims | DECIMAL | % of provider's patients on specialty drugs | Nice-to-Have | 2 - Enhancement | Provider | High-cost Rx signal
Admin / Coding Metrics | denial_rate_overall | 835 Remittance | DECIMAL | % of claims denied (any reason) — overall denial ratio | Yes | 1 - MVP | Provider | Key admin maturity metric
Admin / Coding Metrics | denial_rate_CO | 835 Remittance | DECIMAL | Contractual obligation denial rate (payer responsibility) | Yes | 1 - MVP | Provider | CO adjustment codes
Admin / Coding Metrics | denial_rate_PR | 835 Remittance | DECIMAL | Patient responsibility denial rate | Yes | 1 - MVP | Provider | PR adjustment codes
Admin / Coding Metrics | first_pass_claim_rate | 835 Remittance | DECIMAL | % of claims paid on first submission without rework — coding quality | Yes | 1 - MVP | Provider | Higher = better coding maturity
Admin / Coding Metrics | avg_days_to_submit | Claims Data Warehouse | DECIMAL | Average days from service date to claim submission | Yes | 1 - MVP | Provider | Timely filing signal
Admin / Coding Metrics | rework_rate | 835 / Claims | DECIMAL | % of claims requiring resubmission or appeal | Yes | 1 - MVP | Provider | Lower = better
Admin / Coding Metrics | coding_specificity_score | Claims Data Warehouse | DECIMAL | Ratio of 4th/5th character ICD-10 codes vs unspecified codes | Yes | 1 - MVP | Provider | Higher = more precise coding
Admin / Coding Metrics | modifier_accuracy_rate | Claims vs. Audit | DECIMAL | % of claims with correct modifier usage | Nice-to-Have | 2 - Enhancement | Provider | Requires audit data
Admin / Coding Metrics | prior_auth_compliance | Auth/UM System | DECIMAL | % of services with required prior auth obtained | Nice-to-Have | 2 - Enhancement | Provider
Admin / Coding Metrics | appeal_overturn_rate | Appeals System | DECIMAL | % of denied claims overturned on appeal | Nice-to-Have | 2 - Enhancement | Provider | High rate may indicate initial denial issues
Economic Performance | risk_adjusted_cost_idx | Claims + Member Risk Scores | DECIMAL | Provider's cost relative to expected cost given patient risk mix (O/E ratio) | Yes | 1 - MVP | Provider | Core economic metric; <1.0 = efficient
Economic Performance | cost_trend_12m | Claims Data Warehouse | DECIMAL | Year-over-year cost trend for provider's panel | Yes | 1 - MVP | Provider | Slope of monthly spend
Economic Performance | network_leakage_pct | Claims + Network Config | DECIMAL | % of referrals going out-of-network from this provider | Yes | 1 - MVP | Provider | Network steerage metric
Economic Performance | generic_dispensing_rate | Pharmacy Claims | DECIMAL | % of prescriptions filled as generic vs. brand | Nice-to-Have | 2 - Enhancement | Provider | Rx cost efficiency
Economic Performance | ambulatory_sensitive_admit_rate | Claims Data Warehouse | DECIMAL | Rate of potentially avoidable hospitalizations (AHRQ PQIs) | Nice-to-Have | 2 - Enhancement | Provider | Quality + cost signal
Economic Performance | imaging_utilization_rate | Claims Data Warehouse | DECIMAL | Advanced imaging rate per 1000 members — overuse signal | Nice-to-Have | 2 - Enhancement | Provider | CPT 70000-79999
Economic Performance | total_cost_of_care_pmpy | Claims Data Warehouse | DECIMAL | Total cost of care per member per year for attributed panel | Yes | 1 - MVP | Provider | All-in cost measure
Clustering Features | geo_latitude | NPPES / Geocoding | DECIMAL | Practice location latitude for geo embedding | Yes | 1 - MVP | Provider | Geocoded from address
Clustering Features | geo_longitude | NPPES / Geocoding | DECIMAL | Practice location longitude for geo embedding | Yes | 1 - MVP | Provider | Geocoded from address
Clustering Features | service_area_hhi | Claims Data Warehouse | DECIMAL | Herfindahl-Hirschman Index for provider's service area — market concentration | Nice-to-Have | 2 - Enhancement | Provider | Competition measure
Clustering Features | payer_mix_commercial_pct | Claims Data Warehouse | DECIMAL | % of provider's volume from commercial vs MA vs Medicaid | Yes | 1 - MVP | Provider | LOB mix
Clustering Features | case_mix_index | Claims (DRG-based) | DECIMAL | Average DRG weight — patient complexity | Yes | 1 - MVP | Provider | Institutional providers
Clustering Features | procedure_diversity_idx | Claims Data Warehouse | DECIMAL | Shannon entropy of CPT distribution — service breadth | Nice-to-Have | 2 - Enhancement | Provider
New Drug / Formulary | new_drug_adoption_rate | Pharmacy Claims + FDA | DECIMAL | Rate of prescribing newly approved drugs (within 12m of FDA approval) | Nice-to-Have | 2 - Enhancement | Provider | Innovation vs. cost signal
New Drug / Formulary | formulary_compliance_rate | PBM / Formulary | DECIMAL | % of prescriptions on preferred formulary tier | Nice-to-Have | 2 - Enhancement | Provider | Cost control adherence
New Drug / Formulary | biosimilar_adoption_rate | Pharmacy Claims | DECIMAL | % of eligible prescriptions filled with biosimilar vs. originator biologic | Nice-to-Have | 2 - Enhancement | Provider | Cost savings opportunity
External / Market Data | medicare_cost_report_margin | CMS Cost Reports | DECIMAL | Hospital operating margin from Medicare cost reports | Nice-to-Have | 2 - Enhancement | Facility | Institutional only
External / Market Data | cms_star_rating | CMS Compare | DECIMAL | CMS quality star rating (1-5) for hospitals or MA plans | Nice-to-Have | 2 - Enhancement | Facility | Public data
External / Market Data | hcahps_score | CMS HCAHPS | DECIMAL | Patient satisfaction composite score | Nice-to-Have | 2 - Enhancement | Facility | Public data
External / Market Data | provider_density_per_1000 | NPPES + Census | DECIMAL | Providers per 1000 population in service area — supply factor | Yes | 1 - MVP | ZIP/County
External / Market Data | adi_national_rank | Neighborhood Atlas | INTEGER | Area Deprivation Index for provider's patient population | Nice-to-Have | 2 - Enhancement | ZIP | Contextual SDOH

## Provider Scoring - Project Plan
Task ID | Phase | Week | Day | Task Name | Detailed Description | Deliverable / Output | Owner / Role | Dependencies | Est. Hours | Status
P1.1 | Data & Features | Week 1 | Monday | Extract Provider Master (NPPES) | Download NPPES full replacement file. Extract all active NPI records: NPI, entity type, taxonomy, specialty, practice address (street, city, state, ZIP), hospital affiliations. Geocode addresses (lat/lon). Build provider master dimension table. | Provider master table with NPI, specialty, geo coordinates | Data Engineer | NPPES data access | 8 | Not Started
P1.2 | Data & Features | Week 1 | Monday | Extract Provider Claims Aggregates (12 months) | Aggregate claims by rendering_provider_npi over 12 months: total claims, total allowed/paid, unique members, avg allowed per claim, avg allowed per member. Calculate IP admit rate, ER visit rate, readmit 30-day rate, avg LOS per provider. | Provider claims aggregate table | Data Engineer | Member Scoring complete (for risk scores) | 8 | Not Started
P1.3 | Data & Features | Week 1 | Tuesday | Link Member Risk Scores to Providers | Join Member Risk Score Table to claims by rendering_provider_npi. For each provider, calculate: % of panel flagged CRITICAL/HIGH, average member risk score, distribution of risk tiers across panel. This is the cross-input from member scoring. | Provider-level member risk summary table | Data Scientist | Member Risk Score Table (from Use Case 1) | 6 | Not Started
P1.4 | Data & Features | Week 1 | Wednesday | Build Administrative / Coding Metrics | From 835 remittance data, calculate per provider: overall denial rate, CO/PR/OA denial breakdowns, first-pass claim rate, avg days to submit, rework rate. From claims, calculate coding specificity score (ratio of specific vs unspecified ICD-10 codes). | Admin/coding metrics table per provider | Data Scientist | Tasks P1.1, P1.2 | 8 | Not Started
P1.5 | Data & Features | Week 1 | Thursday | Build Economic Performance Metrics | Calculate risk-adjusted cost index (O/E ratio using member risk scores as expected), cost trend slope (12m), network leakage %, total cost of care PMPY. For institutional providers: case mix index from DRG weights. | Economic performance metrics table per provider | Data Scientist | Tasks P1.2, P1.3 | 8 | Not Started
P1.6 | Data & Features | Week 1 | Friday | Build Clustering Features & Data Quality Audit | Assemble geo features (lat/lon, practice ZIP), specialty taxonomy, payer mix, case mix index, procedure diversity index. Run data quality checks on all provider tables: completeness, distribution analysis, outlier detection. Document issues. | Clustering feature table; data quality audit report | Data Scientist | Tasks P1.1-P1.5 | 8 | Not Started
P2.1 | Model Development | Week 2 | Monday | Provider Clustering — Embedding Generation | Build provider embeddings using features: geo (lat/lon), specialty taxonomy, payer mix, case mix, volume band, cost profile. Apply dimensionality reduction (UMAP or PCA). Run K-means or HDBSCAN clustering. Validate clusters make clinical/business sense (e.g., urban cardiologists, rural PCPs, academic oncologists). | Provider cluster assignments; cluster profiles; embedding visualization | Data Scientist | Task P1.6 | 8 | Not Started
P2.2 | Model Development | Week 2 | Tuesday | Compute Administrative/Coding Maturity Index | Create composite Admin/Coding Maturity Index as weighted score: first_pass_rate (30%), denial_rate inverse (25%), coding_specificity (20%), avg_days_to_submit inverse (15%), rework_rate inverse (10%). Normalize to 0-100 scale. Validate against known high/low performers. | Admin/Coding Maturity Index per provider (0-100) | Data Scientist | Task P1.4 | 6 | Not Started
P2.3 | Model Development | Week 2 | Wednesday | Compute Economic Performance Index | Create composite Economic Performance Index: risk_adjusted_cost_idx (35%), first_pass_rate (15%), denial_rate inverse (15%), network_leakage inverse (10%), readmit_rate inverse (10%), cost_trend inverse (10%), total_cost_of_care_pmpy rank (5%). Normalize to 0-100. Combine with Admin Maturity for overall Provider Risk Score. | Economic Performance Index per provider (0-100); Overall Provider Risk Score | Data Scientist | Tasks P2.1, P2.2, P1.5 | 8 | Not Started
P2.4 | Model Development | Week 2 | Thursday | Provider Risk Tier Assignment & Validation | Assign provider risk tiers: TOP PERFORMER (>80), STANDARD (60-80), WATCH (40-60), CONCERN (<40). Validate against known quality issues, network status, contract performance. Cross-reference with member risk concentration. Sanity check with Medical Director and Network team. | Provider Risk Score Table with tiers; validation report | Data Scientist + Network Team | Task P2.3 | 8 | Not Started
P2.5 | Model Development | Week 2 | Friday | Provider Scoring Output Table & Documentation | Build final provider scoring output table: provider_npi, cluster_id, cluster_name, admin_maturity_idx, econ_perf_idx, overall_risk_score, risk_tier, top_3_drivers, high_cost_member_count, panel_size. Document methodology, weights, thresholds. | Published Provider Risk Score Table; methodology document | Data Scientist | Task P2.4 | 6 | Not Started
P3.1 | Dashboard Integration | Week 3 | Monday | Integrate Provider Scores into Early Warning Dashboard | Add Provider Risk Scoring view to the AEGIS Early Warning Dashboard. Show: provider risk distribution, cluster map (geo heatmap), top CONCERN providers, drill-down to admin maturity and economic performance components. Side-by-side with member risk view. | Dashboard updated with Provider Risk Scoring tab/view | BI Developer | Task P2.5, existing dashboard from Member Scoring | 8 | Not Started
P3.2 | Dashboard Integration | Week 3 | Tuesday | Build Provider-Member Linked View | Create linked drill-down: click a provider to see their CRITICAL/HIGH members, click a member to see their providers. Show which providers have highest concentration of high-cost members. Network leakage visualization. | Provider-Member cross-reference dashboard view | BI Developer | Tasks P3.1, Member Risk Score Table | 8 | Not Started
P3.3 | Dashboard Integration | Week 3 | Wednesday | Build Provider Cluster Analytics View | Visualize provider clusters on map (geo scatter with color by cluster). Show peer comparison within cluster: how does a provider compare to similar peers on admin maturity, economic performance, cost efficiency? Percentile rank within cluster. | Cluster analytics view with peer benchmarking | BI Developer | Task P3.1 | 8 | Not Started
P3.4 | Dashboard Integration | Week 3 | Thursday | Build Scoring Pipeline & Automation | Build automated batch scoring pipeline for provider risk: monthly refresh of claims aggregates, admin metrics, economic metrics. Recalculate scores and update dashboard. Set up PSI monitoring for score drift. | Automated provider scoring pipeline; monthly schedule | ML Engineer | Task P2.5 | 8 | Not Started
P3.5 | Dashboard Integration | Week 3 | Friday | Stakeholder Review — Provider Scoring | Present provider scoring results to Network Management, Contracting, Medical Director, Compliance. Walk through: scoring methodology, sample providers with drill-down, cluster analytics, linked member view. Refine thresholds based on feedback. | Stakeholder feedback; refined thresholds; sign-off | Data Scientist + Project Lead | Tasks P3.1-P3.4 | 8 | Not Started
P4.1 | Go-Live & Ops | Week 4 | Monday | Production Go-Live: Provider Risk Scoring | Execute first production scoring run for provider risk. Validate output completeness. Confirm dashboard views are live. Deliver initial provider risk list to Network Management and Contracting teams. | Provider Risk Scoring LIVE; first scored provider list delivered | Full Team | Tasks P3.1-P3.5 | 8 | Not Started
P4.2 | Go-Live & Ops | Week 4 | Tuesday | Value-Based Contract Integration | Map provider risk scores to existing value-based contracts. Identify providers with CONCERN scores in VBC arrangements — flag for contract review. Build report showing VBC providers by risk tier, economic performance, and quality metrics. | VBC provider risk report; contract review flag list | Data Scientist + Contracting | Task P4.1 | 6 | Not Started
P4.3 | Go-Live & Ops | Week 4 | Wednesday | Provider Outreach Priority List | Generate ranked outreach list for Network team: providers with highest improvement potential (high volume + low admin maturity or low economic performance). Include specific actionable recommendations per provider (e.g., 'coding education needed', 'high OON referral leakage'). | Prioritized provider outreach list with action recommendations | Data Scientist + Network Team | Task P4.1 | 6 | Not Started
P4.4 | Go-Live & Ops | Week 4 | Thursday | Combined Member + Provider Dashboard Training | Train end users on the full AEGIS Early Warning Dashboard: how to navigate member risk view, provider risk view, linked drill-downs, cluster analytics. Create user guide and FAQ. Set up Slack/Teams channel for feedback. | User training completed; user guide document; feedback channel | Project Lead + BI Developer | Tasks P4.1, Member Scoring Go-Live | 6 | Not Started
P4.5 | Go-Live & Ops | Week 4 | Friday | Phase 2 Roadmap — Provider Scoring Enhancements | Document Phase 2 enhancements: (1) Add pharmacy/formulary compliance metrics, (2) CMS Star Rating and HCAHPS integration, (3) Real-time provider alerts, (4) Predictive provider churn model, (5) Network adequacy optimization using clusters, (6) Provider-level SDOH context. | Phase 2 roadmap document; prioritized backlog | Project Lead | Task P4.4 | 4 | Not Started